## Cover
Test Execution Cover Page for DRIVER
Test Summary
| Total Test Case | 125
| OK | 105 | `
| NG | 10
| NA | 10
Release Info
| Application Name | Data for Road Incident Visualization Evaluation and Reporting (DRIVER)
| Start Date | 25-09-2023
| End Date | 27-09-2023
| QA Release Date | 27-09-2023
| Released By | Mahmud Iftekhar Asef
| Verified By | Abdul Quadir

## Revision History
Revision History
SL. | Version | Change | Author | Date | Reviewed by
1 | 1.0.0 | Initial | Mahmud Iftekhar Asef | 26-09-2023 | Abdul Quadir
2 | 1.0.1 | Cover page, Remarks | Mahmud Iftekhar Asef | 27-09-2023 | Abdul Quadir

## Functional
[DRIVER] Fucntional Test Cases for Web Domain
No. | Function Name | No. | Major Category | Minor Category | Test Case Title | Pre-Condition | Test Data | Test Steps | Expected result | Priority | Result | Remark
1 | Log In | LG01 | Log In | Input Fields | Verify that the login page displays blank input fields for both the username and password when initially loaded. | N/A | N/A | 1. Go to https://driver.bjitacademy.com/#!/login 2. Observe the login page's input fields for the username and password. | The input fields of the username and password should be empty when initially loaded. | A | OK
2 | Log In | LG02 | Log In | Log In | Verify that users can successfully log in with valid credentials. | The user is on the DRIVER website login page (https://driver.bjitacademy.com/#!/login) | 1. Username: iftekhar.asef 2. Password: t{8CyQ6lAs5}_C0% | 1. Enter a valid username. 2. Enter a valid password. 3. Click the "Log In" button. | The user should be logged into the system and directed to the dashboard. | C | OK
3 | Log In | LG03 | Log In | Password | Verify that users receive an error message when entering an incorrect password. | The user must be on the DRIVER website login page (https://driver.bjitacademy.com/#!/login) | 1. Username: iftekhar.asef 2. Password: t{8CyQ6lAs5}_C0% | 1. Enter a valid username. 2. Enter a invalid password. 3. Click the "Log In" button. | The system should display an error message indicating that the password is incorrect. | A | OK
4 | Log In | LG04 | Log In | User type | Verify that a user from the "Analyst" group can successfully log in with access of input data, edit and view records. | The user must be on the DRIVER website login page (https://driver.bjitacademy.com/#!/login) | 1. Username of Analyst: iftekhar.asef 2. Password of Analyst: t{8CyQ6lAs5}_C0% | 1. Enter a valid username. 2. Enter a valid password. 3. Click the "Log In" button. 4. Go to "Rcord List" 5. Observe view and edit records functionalities 6. Go to "Add a record" 7. Observe the input data records functionalities | The Analyst user should be logged into the system with the input data, edit and view records functionalities accessible | B | OK
5 | Dashboard | DB01 | DRIVER | Logo | Verfiy that user is directed to the dashboard page upon clicking to the DRIVER logo | User must be logged in to the system | N/A | 1. Clcik "DRIVER" logo 2. Navigate to any other page 3. Clcik "DRIVER" logo again 4. Observe the page | The user should be directed to the dashboard page. | A | OK
6 | Dashboard | DB02 | Black Spots by Severity | Analyze & filter | Verfiy that user is directed to the filter and analyze page upon clicking the "Analyze & filter" of Black Spots by Severity field | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "Analyze & filter" of Black Spot by Severity from Dashboard | The user should be directed to the Black Spot by Severity map page. | A | OK
7 | Dashboard | DB03 | Black Spots by Severity | Analyze & filter | Verify that users can filter & analyze Black Spots by Severity based on severity levels. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "Analyze & filter" of Black Spot by Severity from Dashboard 2. Click "Filter bar" 3. Choose accident severity 4. Click "Done" | Users should filter & analyze Black Spots by Severity based on severity levels | A | NA | Thiis test case is not executable due to the unavailibility of black spots
8 | Dashboard | DB04 | Black Spots by Severity | Zoom in icon | Verify that users can perform "zoom in" to get a closer view of Black Spots on the map. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "Analyze & filter" of Black Spot by Severity from Dashboard 2. Use the "Zoom In" feature on the map interface to zoom in closer to the map | The Black Spots on the map should become more visible, and the map should display a closer view of the locations. | A | NA | Thiis test case is not executable due to the unavailibility of black spots
9 | Dashboard | DB05 | Black Spots by Severity | Zoom out icon | Verify that users can perform "zoom out" to get a broader view of Black Spots on the map. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "Analyze & filter" of Black Spot by Severity from Dashboard 2. Use the "Zoom Out" feature on the map interface to zoom in closer to the map | The Black Spots on the map should remain visible, and the map should display a broader view of the locations. | A | NA | Thiis test case is not executable due to the unavailibility of black spots
10 | Dashboard | DB06 | Black Spots by Severity | An icon to select STREETS & SATELLITE | Verify that Black Spots are visible when viewing the map in Street View. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "Analyze & filter" of Black Spot by Severity from Dashboard 2. Switch the map view to "Street View". 3. Observe the map | The Black Spots on the map should still be visible and identifiable. | A | NA | Thiis test case is not executable due to the unavailibility of black spots
11 | Dashboard | DB07 | Black Spots by Severity | An icon to select STREETS & SATELLITE | Verify that Black Spots are visible when viewing the map in SateliteView. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "Analyze & filter" of Black Spot by Severity from Dashboard 2. Switch the map view to "Satelite View". 3. Observe the map | The Black Spots on the map should still be visible and identifiable. | A | NA | Thiis test case is not executable due to the unavailibility of black spots
12 | Dashboard | DB08 | Incidents: Last Two Weeks map | Mini map | Verify that blue dots representing incidents for the last two weeks are displayed on the mini map of Dashboard. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Observe the mini map of the Dashboard | Mini map should represent incidents that occurred in the last two weeks from the current date on Dashboard | A | NG | #479792
13 | Dashboard | DB09 | Incidents: Last Two Weeks map | View all incidents | Verfiy that user is directed to the map page with all incident as blue dots upon clicking the "View all Incidents" from Dashboard | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "View all incidents" of the "Incidents: Last Two Weeks map" section 2. Observe the all incidents map page | User should be directed to the map page with all incident showing as blue dots | B | OK
14 | Dashboard | DB10 | Incidents: Last Two Weeks map | View all incidents | Verify that the detailed information about the incident is displayed on the "View All Incidents" map upon clicking on a blue dot representing an incident | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "View all incidents" of the "Incidents: Last Two Weeks map" section 2. Click one of the blue dots 3. Click "View" from inicdent details pop up | Pop-up should be displayed with detailed information about the selected incident. | B | OK
15 | Dashboard | DB11 | Total economic loss and societal harm: Last 90 days | Loss amount | Verify that the total economic loss and societal harm for the last 90 days are calculated correctly | User must be logged in to the system & be on the Dashboard Page | Actual Value of total economic loss and societal harm for the last 90 days: BDT47,264Lakhs | 1. Get the value of total economic loss and societal harm for the last 90 days from the section. 2. Match the value with actual value | The total economic loss and societal harm should be calculated accurately and should match the expected values. | A | OK
16 | Dashboard | DB12 | Total economic loss and societal harm: Last 90 days | Detail Loss amount | Verify that clicking on the total amount in the "Total economic loss and societal harm: Last 90 days" section displays detailed loss information. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Navigate to the section that displays Total economic loss and societal harm: Last 90 days 2. Click total amount of "Total economic loss and societal harm: Last 90 days" 3. Observe the change | The total amount should open a detailed view that provides information about economic loss and societal harm broken down by categories. | A | OK
17 | Dashboard | DB13 | Number of incidents | 30 Days | Verify that the total number of incidents that occurred in the last 30 days is showed correctly upon clicking on 30 days. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Navigate to the section that displays the total number of incidents. 2. Click "30 Days". 3. Observe the change. | Total number of incidents should display the total number of incidents that occurred in the last 30 days. | A | OK
18 | Dashboard | DB14 | Number of incidents | 90 Days | Verify that the total number of incidents that occurred in the last 90 days is showed correctly upon clicking on 90 days. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Navigate to the section that displays the total number of incidents. 2. Click on the option for "90 Days." 3. Observe the change | Total number of incidents should display the total number of incidents that occurred in the last 90 days. | A | OK
19 | Dashboard | DB15 | Number of incidents | 365 Days | Verify that the total number of incidents that occurred in the last 365 days is showed correctly upon clicking on 365 days. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Navigate to the section that displays the total number of incidents. 2. Click on the option for "365 Days." 3. Observe the change | Total number of incidents should display the total number of incidents that occurred in the last 365 days. | A | OK
20 | Dashboard | DB16 | Time of Day, Day of Week: Last 90 Days | Day Name | Verify that the left column of the graph(matrix) displays the names of the days of the week properly. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Locate the graph (matrix) for incidents. 2. Check the left column of the graph if the days are visible properly and in the correct order. | The left column of the matrix should display the names of the days of the week in the correct order without any problem. | A | OK
21 | Dashboard | DB17 | Time of Day, Day of Week: Last 90 Days | Time | Verify that the top row of the graph(matrix) displays the time of day properly. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Locate the graph (matrix) for incidents. 2. Check the top row of the graph if the time is visible properly and in the correct order. | The top row of the matrix should display the time of day in the correct order without any problem. | A | OK
22 | Dashboard | DB18 | Saved Filters | Filter Name | Verify that whether filter name is shown correctly in the "saved filter" section | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Locate the Saved Filters section. 2. Click on the filter name field. 3. Select filter name from the list. 4. Observe the filter name of saved filter section | Filter name should be shown correctly in the "saved filter" section | A | OK
23 | Dashboard | DB19 | Saved Filters | Description | Verify that the "saved filters" section displays the previously selected & saved fields correctly in the description | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Locate the Saved Filters section. 2. Observe description of the saved filter section. | The "saved filters" section shuold displays the previously selected & saved fields correctly in the description | B | OK
24 | Dashboard | DB20 | Saved Filters | View | Verify that the "View" button for saved filters redirects the user to the Map page showing all the records with the selected filter applied | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Locate the Saved Filters section. 2. Click on the "View" link for a saved filter. 3. Observe the map with saved filter applied | The user should be directed to the Map page with filtered records of the saved filter. | B | OK
25 | My Account | MA01 | Account Information | N/A | Verify that the account information displayed in the "Account Information" section matches the user's profile data. | User must be logged in to the system | 1. User ID: 93 2. E-mail: iftekhar.asef@bjitacademy.com 3. Administrator: No 4. User Groups: analyst 5. Token: 7a0b17d2ae2f56779d0ab683e775eeb42cc4301a | 1. Navigate to the "Account Information" section. 2. Check the User ID displayed in the Account Information matches the user's actual User ID. 3. Check that the E-mail address displayed in the Account Information matches the user's actual E-mail address. 4. Check that the Administrator status displayed in the Account Information matches whether the user is an admin or not. 5. Check that the User Groups displayed in the Account Information match the groups to which the user belongs. 6. Check that the Token information displayed in the Account Information matches the user's actual Token. | All account information displayed in the "Account Information" section should match the user's actual profile data. | B | OK
26 | Manage Duplicate Records | MDR01 | Potential Duplicate Records | N/A | Verify that the system can correctly identify duplicate data based on a similarity score calculated from time and distance. | User must be logged in to the system | N/A | 1. Navigate to the record creation page 2. Create two records having same occured time and location successfully 3. Navigate to the "Potential Duplicate Records" page 4. Check if the recently created records are shown as potential duplicate records or not. | The system should correctly identify records with similar time and distance attributes as potential duplicate records. | B | NG | #479793
27 | Manage Duplicate Records | MDR02 | Potential Duplicate Records | N/A | Verify that a user can successfully resolve duplicate records by choosing to keep both unique records. | 1. User must be logged in to the system 2. There must be potential at least one pair of duplicate data | N/A | 1. Navigate to the "Potential Duplicate Records" page 2. On the "Potential Duplicate Records" page, click on "Resolve" for a pair of duplicate records. 3. Compare the details of the two records in the popup window. 4. Click on "KEEP BOTH UNIQUE RECORDS." | Both unique records should be kept in the system. | A | NA | This test case is not executable due to failure of test case no MDR01
28 | Manage Duplicate Records | MDR03 | Potential Duplicate Records | N/A | Verify that after resolving duplicate records, there are no duplicate records left in the system. | 1. User must be logged in to the system 2. User has resolved all duplicate records. | N/A | 1. Navigate to the "Potential Duplicate Records" page 2. Check the list of records for any remaining duplicates. | There should be no remaining duplicate records in the system after resolution. | A | NA | This test case is not executable due to failure of test case no MDR01
29 | Manage Duplicate Records | MDR04 | Potential Duplicate Records | N/A | Verify that whether user can successfully resolve duplicate records by choosing to keep one of the duplicate records. | 1. User must be logged in to the system 2. There must be at least one pair of potential duplicate data | N/A | 1. Navigate to the "Potential Duplicate Records" page 2. On the "Potential Duplicate Records" page, click on "Resolve" for a pair of duplicate records. 3. Compare the details of the two records in the popup window. 4. Scroll down and click on "USE THIS RECORD" for the chosen record. | The chosen record should be kept, and the other duplicate record should not be appeared in the system. | A | NA | This test case is not executable due to failure of test case no MDR01
30 | Map | MP01 | Language | N/A | Verify that toggling the language from English to Bangla on the map page changes the language of all fields and labels to Bangla. | User must be logged in to the system & be on the Map Page | N/A | 1. Locate language toggle button 2. Click "Bangla" 3. Check all the fields and lables of the page | All fields, labels, and text elements on the map page should be displayed in the Bangla language after toggling | A | NA | This test case is not executable due to failure of test case no MDR01
31 | Map | MP02 | Filter type | Filter bar | Verify that representation of map is correct upon choosing various filter from filter bar | User must be logged in to the system & be on the Map Page | N/A | 1. Locate the filter bar 2. Select random filters for occurred date, severity, weather etc from filter bar 3. Press Enter 4. Observe the map | Representation of map should be correct after choosing various filters. | B | OK
32 | Map | MP03 | Filter type | Save filter | Verify that users can successfully save a filter from the map page. | User must be logged in to the system & be on the Map Page | N/A | 1. Apply one or more filter from the filter bar. 2. Locate and click on the "Saved Filters" option or button on the map page. 3. A pop-up window should open, displaying existing saved filters (if any). 4. Enter a unique filter name in the "FILTER NAME" input box. 5. Click on the "Save Filter" button within the pop-up window. 6. Verify that the new filter has been successfully saved. | The user should be able to enter a filter name and save it successfully from the map page. | B | OK
33 | Map | MP04 | Filter type | Save filter | Verify that existing saved filters shows the expected result on the map page | 1. User must be logged in to the system & be on the Map Page 2. At least one existing saved filters must be there | N/A | 1. Click on the "Saved Filters" option to access the list of saved filters. 2. Select an existing saved filter from the list by clicking on its name. 3. Observe that the selected saved filter is applied to the map. | The map should refresh and display data according to the selected saved filter's criteria. | B | OK
34 | Map | MP05 | Filter type | Clear filter | Verify that clearing filters removes the added filter and displays the map without any active filters on the map page | User must be logged in to the system & be on the Map Page | N/A | 1. Apply one or more filter from the filter bar. 2. Observe that the map displays filtered data based on the applied filters. 3. Locate and click "Clear Filter" 4. Observe the map to ensure that it displays all data without any active filters applied. | The map should refresh and display all data without any active filters. | B | OK
35 | Map | MP06 | Control Layer Toggle | Radio | Verify that the layer toggle correctly switches to street view from satellite view upon clicking on street view | User must be logged in to the system & be on the Map Page | N/A | 1. Locate and click layer toggle button 2. Click "Street" 3. Observe the map | The map view should be switched to the street view. | A | OK
36 | Map | MP07 | Control Layer Toggle | Radio | Verify that the layer toggle correctly switches to satelite view from street view upon clicking on satelite view | User must be logged in to the system & be on the Map Page | N/A | 1. Locate and click layer toggle button 2. Click "Street" 3. Observe the map | The map view should be switched to the satelite view. | A | OK
37 | Map | MP08 | Control Layer Toggle | Checkbox | Verify that if the user can select multiple checkboxes at a time from the layer toggle | User must be logged in to the system & be on the Map Page | N/A | 1. Locate layer toggle button 2. Click multiple random checkboxes (Incidents/Heatmaps/ Blackspots/DMP Traffic Dvision/DMP Thana) 3. Observe the map | User should click multiple checkboxes and map should be represented according to the selection | C | OK
38 | Map | MP09 | Control Layer Toggle | Checkbox | Verify that if the map representation is correct for selecting different sets of checkboxes from layer toggle for street view | User must be logged in to the system & be on the Map Page | N/A | 1. Locate and click layer toggle button 2. Click "Street" 3. Click multiple random checkboxes (Incidents/Heatmaps/ Blackspots/DMP Traffic Dvision/DMP Thana) 4. Observe the map | The map should be represented correctly as per selection. | B | OK
39 | Map | MP10 | Control Layer Toggle | Checkbox | Verify that if the map representation is correct for selecting different sets of checkboxes from layer toggle for satelite view | User must be logged in to the system & be on the Map Page | N/A | 1. Locate and click layer toggle button 2. Click "Satelite" 3. Click multiple random checkboxes (Incidents/Heatmaps/ Blackspots/DMP Traffic Dvision/DMP Thana) 4. Observe the map | The map should be represented correctly as per selection. | B | OK
40 | Map | MP11 | Zoom in & zoom out icon | Zoom in | Verify that the zoom in icon correctly zooms in the map for various selection of the layer view | User must be logged in to the system & be on the Map Page | N/A | 1. Select a specific layer view (e.g., street view). 2. Click on the "Zoom In" icon. 3. Change the layer view 4. Click on the "Zoom In" icon again. 5. Observe the map | The map should be successfully zoomed in and it should work consistently for various selections of layer views. | B | OK
41 | Map | MP12 | Zoom in & zoom out icon | Zoom out | Verify that the zoom out icon correctly zooms out the map for various selection of the layer view | User must be logged in to the system & be on the Map Page | N/A | 1. Select a specific layer view (e.g., satelite view). 2. Click on the "Zoom Out" icon. 3. Change the layer view 4. Click on the "Zoom Out" icon. 5. Observe the map | The map should be successfully zoomed out and it should work consistently for various selections of layer views. | B | OK
42 | Map | MP13 | Zoom in & zoom out icon | Zoom in | Verify that the zoom in icon correctly zooms in the map after drawing layers(e.g., polygon, rectangle) | User must be logged in to the system & be on the Map Page | N/A | 1. Select a specific layer view (e.g., street view). 2. Draw layers (Polygon/Rectangle) 3. Click on the "Zoom In" icon. 4. Observe the map | The map should be successfully zoomed in. | B | OK
43 | Map | MP14 | Zoom to | N/A | Verify that the "zoom to" successfully zooms in the map based on the searched area | User must be logged in to the system & be on the Map Page | Area name: rampura | 1. Enter area name in zoom to field 3. Click on the "zoom to search" icon. 4. Observe the map | The map should be successfully zoomed in. | B | OK
44 | Map | MP15 | Draw a polygon | N/A | Verify that user can perfectly draw a ploygon on the map | User must be logged in to the system & be on the Map Page | N/A | 1. Click "Draw Polygon" 2. Click on the map to define the vertices of the polygon. 3. Observe the map | User should perfectly draw polygon on map and the drawn polygon should be visible and enclosed | B | OK
45 | Map | MP16 | Draw a polygon | N/A | Verify that representation of map is correct with filtered data upon drawing polygon area | User must be logged in to the system & be on the Map Page | N/A | 1. Apply a any filter from the available filter options. 2. Draw a polygon layer on the map to specify a filtering area. 3. Check that the map displays only the incident data that falls within the drawn polygon area based on the applied filter. 4. Check that the filtered data is accurately represented on the map with appropriate markers. | The map should accurately display only data that occurred within the drawn polygon area based on the selected filter. | B | OK
46 | Map | MP17 | Draw a rectangle | N/A | Verify that user can perfectly draw a rectangle on the map | User must be logged in to the system & be on the Map Page | N/A | 1. Click "Draw rectangle" 2. Hold and drag to draw the rectangle. 3. Observe the map | User should perfectly draw rectangle on map and the drawn rectangle should be visible and enclosed | B | OK
47 | Map | MP18 | Draw a rectangle | N/A | Verify that representation of map is correct with filtered data upon drawing rectangle area | User must be logged in to the system & be on the Map Page | N/A | 1. Apply a any filter from the available filter options. 2. Draw a rectangle layer on the map to specify a filtering area. 3. Check that the map displays only the incident data that falls within the drawn rectangle area based on the applied filter. 4. Check that the filtered data is accurately represented on the map with appropriate markers. | The map should accurately display only data that occurred within the drawn rectangle area based on the selected filter. | B | OK
48 | Map | MP19 | Layer edit | N/A | Verify that edited representation of map is shown upon editing layer of drawn polygon | User must be logged in to the system & be on the Map Page | N/A | 1. Darw a polygon 2. Click "Layer edit" 3. Edit the layer 4. Observe the map | The map representation should be edited after editing polygon layer | B | OK
49 | Map | MP20 | Layer edit | N/A | Verify that edited representation of map is shown upon editing layer of drawn rectangle | User must be logged in to the system & be on the Map Page | N/A | 1. Darw a rectangle 2. Click "Layer edit" 3. Edit the layer 4. Observe the map | The map representation should be edited after editing rectangle layer | B | OK
50 | Map | MP21 | Layer edit | N/A | Verify that Layer edit icon is active after drawing any layer | User must be logged in to the system & be on the Map Page | N/A | 1. Darw a rectangle/polygon layer 2. Observe the layer edit icon | Layer edit button should be active after drawing any layer | A | OK
51 | Map | MP22 | Layer delete | N/A | Verify that the "Layer Delete" button successfully deletes the drawn layer | User must be logged in to the system & be on the Map Page | N/A | 1. Draw a any layer on the map. 2. Locate the "Layer Delete" button on the map interface. 3. Click the "Layer Delete" button. 4. Click "Save" 5. Observe the map to confirm whether the drawn layer is deleted. | The drawn layer on the map should be successfully deleted. | A | OK
52 | Map | MP23 | Footer | Graphs | Verify that the grid view of the graph is correctly shown based on the selected filter. | User must be logged in to the system & be on the Map Page | N/A | 1. Apply a filter to the map to ensure data is available for the graph. 2. Locate and click "Graphs" 3. Click "Grid View" Icon 4. Observe the graph and contents. | The graph should be displayed in grid view based on the applied filter | A | OK
53 | Map | MP24 | Footer | Graphs | Verify that the vertical view of the graph is correctly shown based on the selected filter. | User must be logged in to the system & be on the Map Page | N/A | 1. Apply a filter to the map to ensure data is available for the graph. 2. Locate and click "Graphs" 3. Click "Vertical View" Icon 4. Observe the graph and contents. | The graph should be displayed in vrertical view based on the applied filter | A | OK
54 | Map | MP25 | Footer | Export > Custom report | Verify that the active filters section displays the previously selected filters correctly when generating a custom report | User must be logged in to the system & be on the Map Page | N/A | 1. Apply one or more filters (e.g., filter by date, location, severity, etc.) 2. Click "Export" 3. Select "Custom Report." 4. Observe the pop-up | Active filters section correctly displays the previously selected filters while generating custom report | A | OK
55 | Map | MP26 | Footer | Export > Custom report | Verify that the defined columns and rows are correctly displayed when selecting the "Organize Report by Column" and "Organize Report by Row" options during custom report generation. | User must be logged in to the system & be on the Map Page | Defined columns and roes: Filter: DAY / দিন JUNCTION TYPE / সংযোগ স্থলের ধরণ TRAFFIC CONTROL / ট্রাফিক নিয়ন্ত্রণ ব্যবস্থা COLLISION TYPE / সংঘর্ষের ধরন আঘাত MOVEMENT / গাড়ী চলাচলের দিক DIVIDER? / রোড ডিভাইডার? ROAD GEOMETRY / রাস্তার জ্যামিতিক বিবরণ SURFACE CONDITION / রাস্তার উপরিভাগের অবস্থা SURFACE TYPE / রাস্তার প্রকারভেদ SURFACE QUALITY / রাস্তার প্রকৃতি ROAD CLASS / রাস্তার শ্রেণী ROAD FEATURE / রাস্তার বৈশিষ্ট্য LOCATION TYPE / এলাকার ধরণ VEHICLE REGISTRATION DISTRICT / যানবাহন রেজিস্ট্রেশন জেলা THANA / থানা DRIVING LICENSE DISTRICT / ড্রাইভিং লাইসেন্স জেলা VALID FITNESS CERTIFICATE / বৈধ ফিটনেস সার্টিফিকেট DRIVER SEX / চালকের লিঙ্গ VEHICLE TYPE / যানবাহনের ধরণ VEHICLE MANOEUVRE / যানবাহন চলাচলের ধরন 'DRIVER INJURY / চালকের ক্ষত VEHICLE LOADING / যানবাহনের মালামাল বোঝাই DISTRICT / MET POL / জিলা/মেট্রো পুলিশ VEHICLE DEFECT / যানবাহনের ত্রুটি ALCOHOL / মদ্যপ কিনা? VEHICLE DAMAGE / যানবাহনের ক্ষতি (দুর্ঘটনা জনিত) = SEAT BELT / HELMET / সিট বেল্ট/হেলমেট PASSENGER SEX / যাত্রীর লিঙ্গ PASSENGER INJURY / যাত্রীর ক্ষত PASSENGER POSITION / যাত্রীর অবস্থান PASSENGER ACTION / যাত্রীর কার্যক্রম PEDESTRIAN SEX / পথচারীর লিঙ্গ PEDESTRIAN INJURY / পথচারীর ক্ষত PEDESTRIAN LOCATION / পথচারীর অবস্থান PEDESTRIAN ACTION / পথচারীর কার্যক্রম CONTRIBUTORY FACTOR / সহায়ক কারণ ACCIDENT SEVERITY / দুর্ঘটনার মাত্রা COLLISION TYPE (MOST SEVERE) / সংঘর্ষের ধরন (বেশি মাত্রার টি গ্রহণযোগ্য) CONTRIBUTORY FACTOR / সহায়ক কারণ Other Value (11 JUNCTION TYPE/ARTIST BAKA) TRAFFIC POLICE ZONE / ট্রাফিক পুলিশ জোন TIme: Day Day of Month Day of Week Hour of Day Month Month of Year Week Week of Year Year Geography: DMP Thana/ডিএমপি থানা DMP Traffic Division/ডিএমপি ট্রাফিক বিভাগ | 1. Click "Export" 2. Select "Custom Report." 3. Select "Organize Report by Column." 4. Check that the defined columns are matched with displayed dropdown. 5. Select "Organize Report by Row." 6. Check that the defined rows are matched with displayed dropdown. | The displayed columns and rows should match the defined columns and rows data. | A | OK
56 | Map | MP27 | Footer | Export > Custom report | Verify that the custom report generates the correct rows and columns based on the selected fields when choosing "Organize Report by Column" and "Organize Report by Row" options.. | User must be logged in to the system & be on the Map Page | N/A | 1. Click "Export" 2. Select "Custom Report." 3. Select "Organize Report by Column" from the dropdown 4. Select "Organize Report by Row" from the dropdown 5. Click "Custom Report" 6. Check that the report contains rows and columns based on the selection | Custom report should display rows and columns based on the chosen fields | A | OK
57 | Map | MP28 | Footer | Export > Export CSV | Verify that the system correctly exports recorded incidents in CSV format in a zip file | User must be logged in to the system & be on the Map Page | N/A | 1. Click "Export" 2. select "Export CSV" 3. Click "Download CSV" | A zip file with recorded incidents in CSV format should be downloaded | A | OK
58 | Map | MP29 | Footer | Export > Export CSV | Verify that the "Download CSV" button is not displayed when there is no data to export after cicking "export csv" | User must be logged in to the system & be on the Map Page | N/A | 1. Select an area where there is no data 2. Click "Export" 3. select "Export CSV" | The system should not display a "Download CSV" button. | A | OK
59 | Map | MP30 | Loss amount (In number) | Pop-up view | Verify that the data displayed in the Loss Amount pop-up view changes dynamically upon changing any relevant filters. | User must be logged in to the system & be on the Map Page | N/A | 1. Click "loss amount" from the map page 2. Observe the current loss amount data displayed in the pop-up view. 3. Apply one or more filters 4. Re-check the loss amount data displayed in the pop-up view after applying the filter | The loss amount data in the pop-up view should be updated dynamically based on the filters | B | OK
60 | Map | MP31 | Loss amount (In number) | Pop-up view | Verify that the data displayed in the Loss Amount popup dynamically changes based on the drawn layer upon switching the map layer from "Rectangle" to "Polygon" | User must be logged in to the system & be on the Map Page | N/A | 1. Draw rectangle layer 2. Click "loss amount" 3. Observe the current loss amount data displayed in the pop-up view. 4. Click "Draw Polygon" 5. Draw polygon layer 6. Re-check the loss amount data displayed in the pop-up view after applying the filter | The loss amount data in the pop-up view should be updated dynamically after layer is changed | A | OK
61 | Record List | RL01 | Filter Bar | Occurred Date > From date | Verify that changing only the "From Date" when the "To Date" is already filled shows the expected result | User must be logged in to the system. | From Date: 24/09/2023 | 1. Go to "Record List" 2. Click "Filter Bar" 3. Click "Occurred Date" 4. Click "From Date" 5. Pick any new date from the date picker 6. Click "Done" 7. Observe the Record List | Expected result should be shown after changing the "From Date" | A | NG | #479796
62 | Record List | RL02 | Filter Bar | Occurred Date > From date | Verify that the date picked from the "From Date" date picker shows correctly on the input box as "Month/Date/Year" format | User must be logged in to the system & be on the Record List Page | From Date: 24/09/2023 | 1. Click on the filter bar 2. Click "Occurred Date" 3. Click "From Date" 4. Pick any date from the date picker 5. Observe the date of manual input box of the from date | The date displayed in the manual input box should match the selected date from the date picker and should be in the "Month/Date/Year" format. | A | NG | #479797
63 | Record List | RL03 | Filter Bar | Occurred Date > From date | Verify that if the users can input date for "From Date" using both the date picker and by manually typing dates consecutively. | User must be logged in to the system & be on the Record List Page | From Date: 24/09/2023 | 1. Click on the filter bar 2. Click "Occurred Date" 3. Click "From Date" 4. Pick month and date from the date picker 5. Manually type the year in the input box of the "From Date" field | Users should be able to consecutively input the date using both the date picker and manual input | B | NG | #479798
64 | Record List | RL04 | Filter Bar | Occurred Date > To date | Verify that the "To Date" input field does not allow a date beyond today's date. | User must be logged in to the system & be on the Record List Page | To Date: 26/09/2023 | 1. Click on the filter bar 2. Click "Occurred Date" 3. Click "To Date" 4. Attempt manual input a date that is beyond today's date 5. Attempt input through date picker that is beyond today's date | The "To Date" input field should not accept any input that is beyond today's date. | A | NG | #479799
65 | Record List | RL05 | Filter Bar | Occurred Date > To date | Verify that if the "To Date" input field clears any previously entered date upon clicking the "Clear" button. | User must be logged in to the system & be on the Record List Page | To Date: 26/09/2023 | 1. Click on the filter bar 2. Click "Occurred Date" 3. Click "To Date" 4. Pick any valid date manually or from date picker 5. Click "Clear" | Any previously entered date should be removed from the input field. | A | OK
66 | Record List | RL06 | Filter Bar | Weather | Verify that users can select any weather from the weather list in the "Weather Selection Type" filter. | User must be logged in to the system & be on the Record List Page | Weather: Rain | 1. Click on the filter bar 2. Click "Weather" 3. Select any weather from weather list | The user should be able to select any weather from the weather list | A | OK
67 | Record List | RL07 | Filter Bar | Weather | Verify that selecting a new weather from the weather list overrides any previously selected weather in the "Weather Selection Type" filter. | User must be logged in to the system & be on the Record List Page | 1. Previous weather: Rain 2. New Weather: Fog | 1. Click on the filter bar 2. Click "Weather" 3. Slect any weather from weather list 4. Click "Weather" again 5. Select new weather from the weather list | The previous weather should be overridden with newly selected weather and show the results according to new selection. | A | OK
68 | Record List | RL08 | Filter Bar | SURFACE TYPE / রাস্তার প্রকারভেদ | Verify that selecting a new type of filter does not affect any previously selected type of filter | User must be logged in to the system & be on the Record List Page | SURFACE TYPE / রাস্তার প্রকারভেদ: Brick / ইটের রাস্তা | 1. Click on the filter bar 2. Observe the currently selected filters and their values. 3. Click "SURFACE TYPE / রাস্তার প্রকারভেদ" 4. Slect any SURFACE TYPE / রাস্তার প্রকারভেদ from list 5. Observe the rest of the selection types | Selecting a new type of filter should not affect any previously selected type of filter. | B | OK
69 | Record List | RL09 | Filter Bar | COLLISION TYPE / সংঘর্ষের ধরন আঘাত | Verify that the user gets the result immediately upon selecting any type of filter. | User must be logged in to the system & be on the Record List Page | COLLISION TYPE / সংঘর্ষের ধরন আঘাত: Hit Pedestrian / পথচারীকে আঘাত | 1. Click on the filter bar 2. Observe the currently selected filters and their values. 3. Click "COLLISION TYPE / সংঘর্ষের ধরন আঘাত" 4. Slect any COLLISION TYPE / সংঘর্ষের ধরন আঘাত from list 5. Observe the response | The record list should be changed according to the filter selection immideately after choosing any filter. | A | OK
70 | Record List | RL10 | Filter Bar | ACCIDENT SEVERITY / দুর্ঘটনার মাত্রা | Verify that the list of "ACCIDENT SEVERITY / দুর্ঘটনার মাত্রা" type in the filter bar shows the correct list | User must be logged in to the system & be on the Record List Page | List of defined ACCIDENT SEVERITY / দুর্ঘটনার মাত্রা type: 1. Fatal Accident / মৃত্যু 2. Grievous Accident / মারাত্মক ক্ষত 3. Simple Injury Accident / সাধারণ ক্ষত 4. Motor Collision / মোটর সংঘর্ষ | 1. Click on the filter bar. 2. Click "ACCIDENT SEVERITY / দুর্ঘটনার মাত্রা" 3. Match the list of "ACCIDENT SEVERITY / দুর্ঘটনার মাত্রা" type with defined list | The list of ACCIDENT SEVERITY / দুর্ঘটনার মাত্রা type displayed should match the predefined list | A | OK
71 | Record List | RL11 | Filter Bar | Clear Filters | Verify that clicking the "Clear Filter" button removes all active filters and displays all record data in the record list. | User must be logged in to the system & be on the Record List Page with active filters | N/A | 1. Ensure filters are active. 2. Click "Clear Filter" button 3. Observe the record list | All active filters should be removed displaying all record in the record. | A | OK
72 | Record List | RL12 | Add a record | N/A | Verify that the "Add a Record" button is accessible and functional from the record list page. | User must be logged in to the system & be on the Record List Page | N/A | 1. Locate "Add a Record" button 2. Click "Add a Record" button | The "Add a Record" button should be accessible and functional from the record list page. | A | OK
73 | Record List | RL13 | View | N/A | Verify that clicking the "View" button in the record list displays the corresponding detailed data of the incident. | User must be logged in to the system & be on the Record List Page | N/A | 1. Choose any record to click from record list 2. Click "View" for any record 3. Observe the details of the incident | A pop-up with detailed data of the selected incident should be displayed. | B | OK
74 | Record List | RL14 | View | N/A | Verify that the detailed view of different forms can be accessed from the incident details window. | User must be logged in to the system & be on the Record List Page | N/A | 1. Choose any record to click from record list 2. Click "View" for any record 3. Click any form(e.g., ARF Details, RCF, Details) from the incident details window | The detailed view of the corresponding form should be displayed | A | OK
75 | Record List | RL15 | View | N/A | Verify that clicking the "View" link from the incident details window results in opening the incident details in a new browser window. | User must be logged in to the system & be on the Record List Page | N/A | 1. Choose any record to click from record list 2. Click "View" for any record 3. Click "View" link from the incident details window | The incident details should be opened in a new browser window or tab. | A | OK
76 | Record List | RL16 | Edit | N/A | Verify that the edited data is correctly updated after an incident is edited and "Save Incident" is clicked | User must be logged in to the system & be on the Record List Page | N/A | 1. Choose any record to click from record list 2. Click "Edit" for any record 3. Observe the incident details 4. Change any record details 5. Click "Save Incidents" 6. Click "View" for the recently edited record 7. Observe the incident details. | The edited data should be successfully updated in the system | B | OK
77 | Record List | RL17 | Edit | N/A | Verify that data edited in an incident record persists even after logging out of the application and logging back in. | User must be logged in to the system & be on the Record List Page | N/A | 1. Choose any record to click from record list 2. Click "Edit" for any record 3. Observe the incident details 4. Change any record details 5. Click "Save Incidents" 6. Click "View" for the recently edited record 7. Observe the incident details. 8. Log out of the application 9. Log in again 10. Navigate to the record list page 11. Click "View" for the recently edited record 12. Observe the incident details. | The data should be displayed according to the previous edit. | A | OK
78 | Record List | RL18 | Edit | N/A | Verify that a user can successfully delete an incident from the Edit Incident page. | User must be logged in to the system & be on the Record List Page | N/A | 1. Choose any record to click from record list 2. Click "Edit" for any record 3. Click "Delete Incident" | The selected incident should be successfully deleted from the system | A | OK
79 | Record List | RL19 | Filter Bar | Filter selection | Verify that changing filter selections in the Map page does not affect the filter selections in the Record list page when both pages are open in separate tabs. | 1. User must be logged in to the system. 2. The Map page and Record List page are both opened in separate tabs. | N/A | 1. Go to the record list page tab 2. In the Record List page tab, apply one or more filters from the filter bar 3. Go to map page tab 4. In the Map page tab, apply different filters 5. Return to the Record list page tab 6. Click "Filter Bar" 7. Observe the selected filters | The filter selections in the Record List page tab should remain unchanged | A | NG | #479800
80 | Add a Record | AR01 | Incident Location & Time | Location field | Verify that the mini map correctly zoom the specified location when a valid location field is input. | User must be logged in to the system | Location: Rampura | 1. Click "Add a Record" icon from the top right corner 2. Clcik "Incident Location & Time" 3. Input a valid location in location field 4. Observe the mini map | The mini map should correctly zooms the specified location upon putting a valid location | A | OK
81 | Add a Record | AR02 | Incident Location & Time | Latitude/Longitude | Verify that the longitude and latitude fields are correctly filled upon pointing to an exact location on the mini map. | User must be logged in to the system | Location: Rampura | 1. Click "Add a Record" icon from the top right corner 2. Clcik "Incident Location & Time" 3. Input a valid location in location field 4. Point exact location 5. Observe the longitude and latitude fields | The longitude and latitude fields should be automatically filled with the coordinates of the selected location. | A | OK
82 | Add a Record | AR03 | Incident Location & Time | Occured | Verify that when a user tries to set a date, it cannot be set as a future date. | User must be logged in to the system | Location: Rampura | 1. Click "Add a Record" icon from the top right corner 2. Clcik "Incident Location & Time" 3. Input a valid location in location field 4. Point exact location 5. Attempt to set the occurred date to a future date 6. Observe the behavior | The system should not accept the occurred date of the incident as future date. | A | OK
83 | Add a Record | AR04 | Incident Location & Time | Occured | Verify that when a user tries to set the occurred time of an incident, it cannot be set to a time beyond the present time. | User must be logged in to the system | Location: Rampura | 1. Click "Add a Record" icon from the top right corner 2. Clcik "Incident Location & Time" 3. Input a valid location in location field 4. Point exact location 5. Select occurred date as today 6. Attempt to set the occurred time to a future time 7. Observe the behavior | The system should not accept the occurred time of the incident as future time. | A | OK
84 | Add a Record | AR05 | Incident Location & Time | Expand | Verify that expanding another form within the "Add a Record" page does not affect the data entered in the "Incident Location & Time" section. | User must be logged in to the system | 1. Location: Rampura 2. Weather: Rain 3. Light: Dusk | 1. Click "Add a Record" icon from the top right corner 2. Clcik "Incident Location & Time" 3. Input all data 4. Expand any other form. 5. Expand "Incident Location & Time" again 6. Check the input fields | The data entered in the "Incident Location & Time" section should remain unchanged | A | OK
85 | Add a Record | AR06 | Incident Location & Time | Incident Images | Verify that whether previously selected pictures are not removed from the field upon clearing them from image preview | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Locate "Incident Images" from "Incident Location & Time" 4. Click "Choose File" 5. Pick single/multiple images. 6. Clear the image previews 7. Check the selected images field | Selected pictures should not be removed. | A | OK
86 | Add a Record | AR07 | Incident Location & Time | Incident Images | Verify that the Incident Images field allows users to upload multiple pictures at a time as input. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Locate "Incident Images" from "Incident Location & Time" 4. Click "Choose File" 5. Pick multiple images at a time. 6. Check the image selection | Users should be able to upload multiple pictures at a time as input. | A | OK
87 | Add a Record | AR08 | Incident Location & Time | Incident Images | Verify that if clicking the "Cancel" button in the file picker window removes all the previously selected images. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Locate "Incident Images" from "Incident Location & Time" 4. Click "Choose File" 5. Pick single/multiple images 6. Click "Choose File" again 7. Click "Cancel" 8. Check Incident Image field. | All the previously selected images should be removed upon clicking "Cancel" | A | OK
88 | Add a Record | AR09 | RCF (Road Crash Form) | Expand | Verify that clicking on the expanding arrow for the RCF (Road Crash Form) form expands only the RCF form. | User must be logged in to the system | N/A | 1. Click "Add a Record" icon from the top right corner 2. Clcik "Incident Location & Time" 3. Click "Expand arrow" of RCF. 5. Observe the page | Only the RCF form should be expanded | A | OK
89 | Add a Record | AR10 | RCF (Road Crash Form) | LOCATION SKETCH / নকশা/ খসরা চিত্র | Verify that image preview is displayed after selection of pictures for "Location Sketch" field | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "RCF Details" Expand button 4. Locate "LOCATION SKETCH / নকশা/ খসরা চিত্র" 5. Click "Choose File" 6. Pick a image file 7. Check the "LOCATION SKETCH / নকশা/ খসরা চিত্র" field | Image previews should be displayed for selected pictures | A | OK
90 | Add a Record | AR11 | RCF (Road Crash Form) | LOCATION SKETCH / নকশা/ খসরা চিত্র | Verify that whether previously selected image's preview is removed from the location sketch field upon clicking "Cancel" on the file picker window | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "RCF Details" Expand button 4. Locate "LOCATION SKETCH / নকশা/ খসরা চিত্র" 5. Click "Choose File" 6. Pick a image file 7. Click "Choose File" again 8. Click "Cancel" 9. Check Location Sketch field. | The previously selected image's preview should be removed | A | NG | #479801
91 | Add a Record | AR12 | RCF (Road Crash Form) | Number Field | Verify that the number field within the RCF (Road Crash Form) form accepts values only within the range of 0 to 100. | User must be logged in to the system | 1. Lower Boundary Value: 0 2. In range value: 65 3. Upper Boundary value: 100 | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "RCF Details" Expand button 4. Locate "CASUALTIES NUMBER OF DEAD / দুর্ঘটনায় হতাহত মৃতের সংখ্যা" 5. Insert lower boundary value 6. Insert in range value 7. Insert upper boundary value | The number field should accept values only within the range of 0 to 100. | A | OK
92 | Add a Record | AR13 | RCF (Road Crash Form) | Number Field | Verify that the number field within the RCF (Road Crash Form) form does not accept any value upper than 100 | User must be logged in to the system | Input value: 101 | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "RCF Details" Expand button 4. Locate "CASUALTIES NUMBER OF DEAD / দুর্ঘটনায় হতাহত মৃতের সংখ্যা" 5. Input any value upper than 100 | The number field should accept values only within the range of 0 to 100. | A | OK
93 | Add a Record | AR14 | RCF (Road Crash Form) | Contributory factor | Verify that users can select multiple contributory factors in the RCF form. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "RCF Details" Expand button 4. Locate "CONTRIBUTORY FACTOR / সহায়ক কারণ" 5. Check multiple checkboxes | Users should select multiple contributory factors in the RCF form | A | OK
94 | Add a Record | AR15 | ARF (Accident Report Form) | THANA / থানা | Verify that typing the correct Thana number selects the corresponding Thana in the ARF form | User must be logged in to the system | Thana number: 10 | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "ARF Details" Expand button 4. Locate and click "THANA / থানা" 5. Input Thana number 6. Check thana field | Typing the correct Thana number should select the corresponding Thana | B | OK
95 | Add a Record | AR16 | ARF (Accident Report Form) | THANA / থানা | Verify that the Thana selected by the user is displayed in the Thana field of the ARF Form. | User must be logged in to the system | Thana: Lalbag | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "ARF Details" Expand button 4. Locate "THANA / থানা" 5. Select any thana from the dropdown 6. Check the "THANA / থানা" field | Thana selected by the user should be displayed in the Thana field of the ARF Form. | B | OK
96 | Add a Record | AR17 | ARF (Accident Report Form) | THANA / থানা | Verify that a user can correctly override a previously selected "Thana" by typing a new "Thana Number" in the respective field. | User must be logged in to the system | Thana: Lalbag | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "ARF Details" Expand button 4. Locate and click "THANA / থানা" 5. Input Thana number 6. Check thana field 7. Input new thana number 8. Check thana field | Typing the correct Thana number should select the corresponding Thana | B | NG | #479802
97 | Add a Record | AR18 | ARF (Accident Report Form) | NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা | Verify that the "NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা" field accepts input within the range of 0 to 150. | User must be logged in to the system | 1. Lower Boundary Value: 0 2. In range value: 65 3. Upper Boundary value: 150 | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "ARF Details" Expand button 4. Locate "NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা" 5. Insert lower boundary value 6. Insert in range value 7. Insert upper boundary value | The "NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা" field should accept input within the range of 0 to 150. | A | NG | #479803
98 | Add a Record | AR19 | ARF (Accident Report Form) | NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা | Verify that the "NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা" field does not accept any character other than number | User must be logged in to the system | Input data: a2s3@d# | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "ARF Details" Expand button 4. Locate "NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা" 5. Input any character other than number | The "NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা" field should not accept any character other than numbers | A | OK
99 | Add a Record | AR20 | ARF (Accident Report Form) | VEHICLES / যানবাহনগুলি | Verify that clicking the "Add Vehicle" button adds another Vehicle section dynamically after filling in details for vehicle 1. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "VEHICLES / যানবাহনগুলি" Expand button 4. Add vehicle 1 5. Fill the details of vehicle 1 6. Click "Add Vehicle" 7. Check the "VEHICLES / যানবাহনগুলি" section | Vehicle 2 should be created | A | OK
100 | Add a Record | AR21 | ARF (Accident Report Form) | PASSENGER / যাত্রীদের বিবরণ | Verify that the "Delete Passenger" button correctly removes the corresponding passenger from the passenger section. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "PASSENGER / যাত্রীদের বিবরণ" Expand button 4. Add passenger 1 5. Add passenger 2 6. Delete passenger 2 7. Check the "PASSENGER / যাত্রীদের বিবরণ" section | Corresponding passenger should be removed from the passenger section successfully | A | OK
101 | Add a Record | AR22 | ARF (Accident Report Form) | PASSENGER / যাত্রীদের বিবরণ | Verify that the serial numbers of the passengers are automatically adjusted if any passenger is deleted from the list. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "PASSENGER / যাত্রীদের বিবরণ" Expand button 4. Add passenger 1 5. Add passenger 2 6. Add passenger 3 7. Remove passenger 2 8. Check the passengers' serial number | The serial numbers of the passengers should be automatically adjusted upon deleting. | A | OK
102 | Add a Record | AR23 | ARF (Accident Report Form) | PEDESTRIAN / পথচারীদের বিবরণ | Verify that the data filled in the "PEDESTRIAN / পথচারীদের বিবরণ" form remains unaffected when the form is collapsed and then expanded again. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "PEDESTRIAN / পথচারীদের বিবরণ" Expand button 4. Add Pedestrain 5. FIll details 6. Click PEDESTRAIN collapse button 7. Click PEDESTRAIN Expand button again 8. Check the data fields | The data entered into "PEDESTRIAN / পথচারীদের বিবরণ" form should be unchanged. | A | OK
103 | Add a Record | AR24 | ARF (Accident Report Form) | CONTRIBUTORY FACTOR / সহায়ক কারণ | Verify that selecting a "Other / অন্যান্য" from" CONTRIBUTORY FACTOR / সহায়ক কারণ" immediately provides an input field to write additional details. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Click "CONTRIBUTORY FACTOR / সহায়ক কারণ" Expand button 4. Check the "Other / অন্যান্য" checkbox | An input field should immediately appear allowing the user to provide additional details | A | OK
104 | Add a Record | AR25 | Save Incident | N/A | Verify that clicking the "Save Incident" button correctly saves the incident record in the record list. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Add all mandatory fields with valid data 4. Click "Save Incident" 5. Go to Record list | The incident details should be saved and should be visible in the record list. | C | OK
105 | Add a Record | AR26 | Save Incident | Validation | Verify that after clicking the "Save Incident" button error message is displayed if any mandatory field is not filled. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Add necessary fields 4. Click "Save Incident" | Error message should be displayed and the incident should not be saved. | A | OK
106 | Add a Record | AR27 | Cancel | N/A | Verify that clicking the "Cancel" button during the "Add a Record" process cancels the operation and returns the user to the previous page. | User must be logged in to the system | N/A | 1. Go to map/record list page 2. Click "Add a Record" 3. Fill some fields 4. Click "Cancel" | The user should be returned to the previous page without any changes being saved. | A | OK

## GUI
[DRIVER] GUI Test Cases for Web Domain
No. | Function Name | No. | Major Category | Minor Category | Test Case Title | Pre-Condition | Test Data | Test Steps | Expected result | Priority | Result | Remark
1 | Log In | G_LG01 | Log In | Text Content | Verify that the text content on the login page of the DRIVER application appears correctly. | The user is on the DRIVER website login page (https://driver.bjitacademy.com/#!/login) | N/A | 1. Observe the Log In page | The text content on the login page, including headings, labels, button text should appear correctly, without any visual defects. | A | OK
2 | Dashboard | G_DB01 | DRIVER | Logo | Verify that the DRIVER logo is correctly positioned in the upper left corner of the page | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Observe the top-left corner of the dashboard | The DRIVER logo should be visibly and consistently placed in the upper left corner of the page | A | OK
3 | Dashboard | G_DB02 | Black Spots by Severity | Black Spots | Verify that the default view of the Black Spots by Severity is displayed on the map with the appropriate markers. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "Analyze & filter" of Black Spot by Severity from Dashboard 2. Observe the Black Spot by Severity map | By default, Black Spots on the map should be displayed as markers indicating severity. | A | NA | Thiis test case is not executable due to the unavailibility of black spots
4 | Dashboard | G_DB03 | Incidents: Last Two Weeks map | Section | Verify that the "Incidents: Last Two Weeks" section is available on the Dashboard Page. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Observe "Incidents: Last Two Weeks" from Dashoard | The "Incidents: Last Two Weeks" section should be visible on the Dashboard Page. | A | OK
5 | Dashboard | G_DB04 | Total economic loss and societal harm: Last 90 days | Section | Verify that the "Total Economic Loss and Societal Harm: Last 90 Days" section is correctly placed on the dashboard page | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Observe "Total Economic Loss and Societal Harm: Last 90 Days" from Dashoard | The "Total Economic Loss and Societal Harm: Last 90 Days" section should be correctly positioned on the dashboard page | A | OK
6 | Dashboard | G_DB05 | Number of incidents | N/A | Verify that clicking on the options for "30 Days," "90 Days," and "365 Days" seamlessly displays the total incidents in the "Number of incidents" section without delays | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "30 Days" on "Number of incidents" section 2. Click "90 Days" on "Number of incidents" section 3. Click "365 Days" on "Number of incidents" section 4. Observe the change | The application should seamlessly and without any delays display the total incidents for each selected time duration on the "Number of incidents" section | A | OK
7 | Dashboard | G_DB06 | Number of incidents | Highlight | Verify that hovering over the links for different durations (30 days, 90 days, 365 days) highlights them properly. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Hover the mouse cursor over the "30 days" link on "Number of incidents" section 2. Hover the mouse cursor over the "90 days" link on "Number of incidents" section 3. Hover the mouse cursor over the "365 days" link on "Number of incidents" section 4. Observe the change | Each link should be highlighted with visual change | A | OK
8 | Dashboard | G_DB07 | Time of Day, Day of Week: Last 90 Days | Event count mark | Verify that the colored boxes representing incidents in the graph(matrix) are displayed without any glitches. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Locate the graph (matrix) for incidents. 2. Inspect the colored boxes in the matrix to ensure that they are displayed properly and without any graphical glitches. | The colored boxes in the matrix should be displayed without any visual glitches | A | OK
9 | Dashboard | G_DB08 | Time of Day, Day of Week: Last 90 Days | Event count mark | Verify that the colors used to represent severity in the graph(matrix) are consistent with the defined color-code | User must be logged in to the system & be on the Dashboard Page | 1. Defined Color Code for High severity: #804600 2. Defined Color Code for Medium severity: #BF6900 3. Defined Color Code for Low severity: #FF8C00 | 1. Locate the graph (matrix) for incidents. 2. Examine the colored boxes in the matrix to determine their severity levels based on color. 3. Match the predefined color-code for severity | The colors used to represent severity in the graph matrix should be consistent with the defined color-codes based on severity | A | OK
10 | Map | G_MP01 | Zoom in & zoom out icon | Icon | Verify that the "Zoom In" and "Zoom Out" icons are placed together in the expected location on the map interface. | User must be logged in to the system & be on the Map Page | N/A | 1. Locate and observe "Zoom In" and "Zoom Out" icons. 2. Check whether both the "Zoom In" and "Zoom Out" icons are located together on the defined place. | The "Zoom In" and "Zoom Out" icons should be placed together on proper place | A | OK
11 | Map | G_MP02 | Draw a polygon | Lines | Verify that lines are drawn between consecutive vertices upon clicking for the vertices creation when drawing a polygon on the map. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Click "Draw a polygon" 2. Click on the map to create the first vertex of the polygon. 3. Click on a different location on the map to create a second vertex. 4. Check that a line is drawn between the first and second vertices. 5. Continue to click on additional locations on the map to create more vertices. 6. Check that lines are drawn between consecutive vertices, forming the polygon's shape. | The map should display lines connecting consecutive vertices and continuous vertex creation should be allowed until the polygon is complete. | A | OK
12 | Map | G_MP03 | Layer edit | Icon | Verify that "Layer edit" icon is in proper position and initially in a disabled state. | User must be logged in to the system & be on the Dashboard Page | N/A | 1. Locate the "Layer Edit" button on the map interface. 2. Check the position of the "Layer Edit" button on the map page. 3. Check the initial state of the "Layer Edit" button. | The "Layer Edit" button should be positioned at proper place on the map page and initially be in a disabled state | A | OK
13 | Map | G_MP04 | Footer | Graphs | Verify that the colored bars of the vertical view displays correct predefined color. | User must be logged in to the system & be on the Dashboard Page | Defined Color-code for vertical bars: #6495ED | 1. Apply a filter to the map to ensure data is available for the graph. 2. Locate and click "Graphs" 3. Click "Vertical View" Icon 4. Examine the colored bars in the vertical view to determine. 3. Match the predefined color-code with bar's color. | The colored bars of the vertical view should display correctly as predefined color. | A | OK
14 | Record List | G_RL01 | Filter Bar | Add a record | Verify that the "Add a Record" button is displayed properly with a plus icon in the middle of it. | User must be logged in to the system & be on the Record List Page | N/A | 1. Locate the "Add a Record" button on the page. 2. Observe the icon of "Add a Record" button. | The "Add a Record" button should be accessible and functional from the record list page. | A | OK
15 | Record List | G_RL02 | Filter Bar | View | Verify that there is a "New Window" icon displayed on the left side of the "View" link in the incident details window. | User must be logged in to the system & be on the Record List Page | N/A | 1. Choose any record to click from record list 2. Click "View" for any record 3. Observe the view link on the top right corner of incident details window | A "New Window" icon should be visible on the left side of the "View" link in the incident details window. | A | OK
16 | Record List | G_RL03 | Filter Bar | View | Verify that the "View" and "Edit" buttons for each incident record in the Record List are correctly positioned side by side. | User must be logged in to the system & be on the Record List Page | N/A | 1. Observe the "View" and "Edit" button for each record of the record list page. | The "View" and "Edit" buttons should be positioned correctly side by side for each incident | A | OK
17 | Record List | G_RL04 | Navgiation Bar | N/A | Verify that the navigation bar remains sticky at the top of the page when the user scrolls down. | User must be logged in to the system & be on the Record List Page | N/A | 1. Scroll down the page. 2. Observe the behavior of the navigation bar as you scroll. | The navigation bar should remain fixed at the top of the page. | A | OK
18 | Add a Record | G_AR01 | VEHICLES / যানবাহনগুলি | Button | Verify that if the "Add Vehicle" button is correctly positioned in vehicles section | User must be logged in to the system & be on the Record List Page | N/A | 1. Click "Add a Record" from the top right corner of tha page 2. Click vehicles expand button 3. Observe the "add vehicle" button | The "Add Vehicle" button should be correctly positioned in vehicles section | A | OK
19 | Add a Record | G_AR02 | Save Incident/Cancel | Button | Verify that the "Save Incident" and "Cancel" buttons remain in a fixed position together on the page and do not change their relative positions when scrolling. | User must be logged in to the system & be on the Record List Page | N/A | 1. Click "Add a Record" from the top right corner of tha page 2. Scroll down 3. Scroll up 4. Observe both the buttons | The "Save Incident" and "Cancel" buttons should remain fixed in their original position. | A | OK

## Notes
Notes
Test Results
For the test results, it will basically following rules.
・Date confirmed
・Confirmation's name
・Confirmation terminal
It described to confirm the daily.
・Test results
Is, "OK", "NG", "NA".
「OK」：If the operation of the expected behavior as could be confirmed
「NG」：If the operation of the expected behavior could not be confirmed
「NA」：If the test carried out is not possible/ Not executed.
※ NG Detailed generating procedure of the bug is recoreded in Redmine with appropiate test evidence.
・Test priority
Is, "A", "B", "C","D".
「A」：Normal
「B」：High
「C」：Urgent
「D」：Immediate