## Cover
QA Report
Sprint | : | 1
Project | : | DRIVER
Build | : | 1.0.0
Date | : | 27-Sept-23
Reporter | : | Mahmud Iftekhar Asef

## Release Summary
DRIVER Release Summary Report
Release Info |  | Browser & Device List
Release Name | 1.0.0 | # | Desktop web Browser | Version
Version Name | 1.0.0 | 1 | PC(Windows) | Windows 11
Release Topic | Login Dashboard My Account Manage Duplicate Records Map Record List Add a record | 2 | Google Chrome | 117.0.5938.92
Start Date | 25-09-2023
End Date | 27-09-2023
QA Release Date | 27-09-2023
Release Status | N/A
Released By | Mahmud Iftekhar Asef
Prepared By | Mahmud Iftekhar Asef
Verified By | Abdul Quadir
Executed Test Type:
1 | Functional
2 | GUI
Non Executed Test Type:
1 | Security Testing
2 | Integration Testing
3 | Regression Testing
4 | Retesting
5 | Performance
6 | Ad-hoc testing
7 | Unit testing
8 | Acceptance Testing
9 | Device Compatibility

## Functionality Verification
DRIVER Release Checklist
# | Module | TL Confirmation | Verified by QA | Status (by QA) | TL Comment | QA Comment
1 | Login | Yes | Yes | OK
2 | Dashboard | Yes | Yes | NG |  | #479792
3 | My Account | Yes | Yes | OK |  | Ok
4 | Manage Duplicate Records | Yes | Yes | NG |  | #479793
5 | Map | Yes | Yes | OK |  | Ok
6 | Record List | Yes | Yes | NG |  | #479796 #479797 #479798 #479799 #479800
7 | Add a Record | Yes | Yes | NG |  | #479801 #479802 #479803

## Graphical Report
Test Case Execution Report
| Build Version No: | 1.0.0
| Total Test cases: | 125
| Test Environments (Browsers): | 1
| Total Executable test cases: | 115
| Test Cases Executed: | 115
| Passed: | 105
| Failed: | 10
| NA: | 10
| WIP: | 3
| Total Reported Bugs : | 10
| New | 10
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Blocker | 0
| Critical | 0
| Major | 2
| Minor | 8
| Trivial | 0
| Total: | 10
| Reported Bugs : (All Sprints) | 10
| New | 10
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Low | 3
| Medium | 7
| High | 0
| Urgent | 0
| Immediate | 0
| Total: | 10
Step-2: Sprint#1 Bug summary
Step-2: Sprint#1 Bugs Severity:
Total Bug summary
Total Bugs (Priority wise):

## Bug_list
Sprint#1 Bug List
Bug Type | Quantity
UI: | 0
Functional: | 10
Total: | 10
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | N/A | N/A | N/A | N/A | N/A
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | #479792 | [Dashboard][Incidents: Last Two Weeks map] Blue Dots for Incidents in “Incidents: Last Two Weeks” mini map is not displayed Dashboard | New | Medium | Minor
2 | #479793 | [Manage Duplicate Records][Potential Duplicate Records] The system is not correctly identifying duplicate data based on a similarity score calculated from time and distance. | New | High | Minor
3 | #479796 | [Record List][Filter Bar] When the filter bar is in its default state and the "From Date" is changed, it does not affect the record list even if the "To Date" is already filled. | New | Medium | Major
4 | #479797 | [Record List][Filter Bar] The "From Date" date picker in the occurred date of the filter bar displaying dates in the "Date/Month/Year" format instead of the expected "Month/Date/Year" format. | New | Low | Minor
5 | #479798 | [Record List][Filter Bar] In the "From Date" field of the occurred date filter bar, manually typing a date, month, or year after picking any date from the date picker does not consistently work as expected. | New | Medium | Minor
6 | #479799 | [Record List][Filter Bar] In the "To Date" field of the occurred date filter bar, the input field allows users to input dates that are beyond today's date. | New | Low | Minor
7 | #479800 | [Record List][Filter Bar] Changing filter selections in the “Map” page affects the filter selections in the “Record List” page upon clicking the filter bar when these two pages are open together in separate tabs of the browser. | New | Medium | Major
8 | #479801 | [Add a Record][RCF] Image preview of previously selected image persists in the "Location Sketch" field of RCF form even after successfully canceling the image selection in the file picker window. | New | Medium | Minor
9 | #479802 | [Add a Record][ARF] in ARF form when any previous thana bigger than 5 is already selected, manually typing single-digit Thana numbers (e.g., 4, 5) into the Thana field does not accurately select the corresponding Thana | New | Medium | Minor
10 | #479803 | [Add a Record][ARF] The "NUMBER OF DRIVER CASUALTIES / ড্রাইভারের সংখ্যা" field in ARF form does not accept any value bigger than 100. | New | Medium | Minor
Functional Bugs:
Step-1: Sprint#1- Bug summary
UI Bugs:

## Bug_trend
Sprint | Test case | Bugs | Resolved | Trend
Sprint#1 | 125 | 10 | 0% | 0%

## Defect density
Sprint | Effort | Defect | Defect density | Defect density
Sprint#1 | 1 | 10 | 1000% | 1000%